## Homepage
VISWANTHI DESIGNS
TESTED BY:KRISHNA .K.B OS: WINDOWS 11 |  |  |  | VERIFIED BY:RAKHY DATE:05/08/2024 MODULE NAME:HOME PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXCEPTED RESULT | ACTUAL RESULT | STATUS
VD_HP_01 | verify that user can open Viswanthi designs site | 1.open viswanthi designs.com site. | https://viswanthi.com/ | user should be able to open site | user is able to open site | pass
VD_HP_02 | check whether splash screen available or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | user should see the splash screen | user cannot see the splash screen | fail
VD_HP_03 | ensure the logo is present or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should show logo | user can see the logo | pass
VD_HP_04 | verify that banner's alignment is correct or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | image should be aligned properly | image is aligned properly | pass
VD_HP_05 | check whether the banner image slider is working or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | banner image slider shoukd be properly | image slider is working | pass
VD_HP_06 | verify the shop now button on banner is working or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | button should work | button is working properly | pass
VD_HP_07 | verify menu icon is working or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | menu icon should work | icon is working | pass
VD_HP_08 | check whether search field contain voice search availability or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should contain voice serach availability in search field | not contain voice search | fail
VD_HP_09 | check whether search field contain image search or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should contain image search | not contain image search | fail
VD_HP_10 | verify all device shows search button | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should show search button | search button is showing | pass
VD_HP_11 | verify the menu shows all the options as per the srs document | 1.open viswanthi designs.com site. | https://viswanthi.com/ | Menu should show all the options | menu shows all the option | pass
VD_HP_12 | verify the search icon is working | 1.open viswanthi designs.com site. | https://viswanthi.com/ | button should work | button is working properly | pass
VD_HP_13 | verify the search bar by inputing invalid inputs | 1.open viswanthi designs.com site. | https://viswanthi.com/ | search bar should not accept invalid inputs | search bar is not accepting invalid input | pass
VD_HP_14 | verify the links in popular searches are working or not | 1.open viswanthi designs.com site. 2. click on search bar 3.click on the given popular search links (sweaters,shirts) | https://viswanthi.com/ | search links should give results | no results are showing | fail
VD_HP_15 | verify the close icon near the search bar is working or not | 1.open viswanthi designs.com site. 2.click on the search icon 3.click on the close icon | https://viswanthi.com/ | close icon should close search window. | close icon is working | pass
VD_HP_16 | check whether after clicking the particular item it directly redirecting to the particular page | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should redirect from home page | redirecting the page | pass
VD_HP_17 | check whether every product contain it's price details | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should contain price details to each product | constains price details | pass
VD_HP_18 | check whether every product contain add to cart options | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should contain add to cart option | constains add to cart details | pass
VD_HP_19 | check whether list of product is showing or not | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should display list of products | list of products are showing | pass
VD_HP_20 | check whether the quick view icon in each product is working. | 1.open viswanthi designs.com site. 2. click on the quick view icon of any product | https://viswanthi.com/ | quick view of product should be shown | quick view of product is showing | pass
VD_HP_21 | check whether the site works in all platform | 1.open viswanthi designs.com site. | https://viswanthi.com/ | should open site on all platform | site open in all platform | pass
VD_HP_22 | verify by clicking on the logo redirects to home page | 1.open viswanthi designs.com site. 2. click on the logo. | https://viswanthi.com/ | it should redirects to home page | clicking on logo redirects to home page | pass
VD_HP_23 | verify by clicking on the cart icon | 1.open viswanthi designs.com site. 2. click on the cart icon | https://viswanthi.com/ | it should redirects to cart page | it is redirecting to cart page | pass
VD_HP_24 | verify by clicking on the wishlist icon | 1.open viswanthi designs.com site. 2.click on the wishlist icon | https://viswanthi.com/ | wishlist window should appear | wishlist window appears | pass
VD_HP_25 | verify the return to shop button in wishlist page is working or not | 1.open viswanthi designs.com site. 2.click on thw wishlist icon 3. click on the return to shop button | https://viswanthi.com/ | it should redirect to the pevious page | redirecting to the previous page | pass
VD_HP_26 | verify the arrow icon in wishlist page is working or not | 1.open viswanthi designs.com site. 2.click on the wishlist icon 3. click on the arrow icon | https://viswanthi.com/ | it should redirect to the pevious page | redirecting to the previous page | pass
VD_HP_27 | verify the arrow icon in cart page is working or not | 1.open viswanthi designs.com site. 2.click on the cart icon 3. click on the arrow icon | https://viswanthi.com/ | it should redirect to the pevious page | redirecting to the previous page | pass
VD_HP_28 | verify by clicking on the compare icon | 1.open viswanthi designs.com site. 2.click on the compare icon | https://viswanthi.com/ | compare window should appear | compare window appears as expected | pass
VD_HP_29 | verify by clicking on the close icon in compare window | 1.open viswanthi designs.com site. 2.click on the compare icon 3.click on the close icon | https://viswanthi.com/ | it should close the window | close icon is working | pass
VD_HP_30 | verify the recently viewed icon is working | 1.open viswanthi designs.com site. 2.click on the recently viewed icon | https://viswanthi.com/ | it should display the recently viewed products | it is displaying recently viewed products | pass
VD_HP_31 | verify by clicking on shop link in nav bar | 1.open viswanthi designs.com site. 2.click on the shop | https://viswanthi.com/ | it should redirects to shop page | it is redirecting to shop page | pass
VD_HP_32 | verify by clicking on about link in nav bar | 1.open viswanthi designs.com site. 2.click on the about | https://viswanthi.com/ | it should redirects to about page | it is redirecting to about page | pass
VD_HP_33 | verify by clicking on order tracking link in nav bar | 1.open viswanthi designs.com site. 2.click on the order tracking | https://viswanthi.com/ | it should redirects to order tracking page | it is redirecting to order tracking page | pass
VD_HP_34 | verify by clicking on my account link in nav bar | 1.open viswanthi designs.com site. 2.click on the my account | https://viswanthi.com/ | it should redirects to my account page | it is redirecting to my account page | pass
VD_HP_35 | verify the whatsapp icon is working or not | 1.open viswanthi designs.com site. 2.click on the whatsapp icon | https://viswanthi.com/ | it should redirects to whatsapp chat page | it is redirecting to whatsapp chat page | pass

## Shop Page
VISWANTHI DESIGNS
TESTED BY:KRISHNA .K.B OS: WINDOWS 11 |  |  |  | VERIFIED BY:RAKHY DATE:05/08/2024 MODULE NAME:SHOP PAGE
SHOP PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXCEPTED RESULT | ACTUAL RESULT | STATUS
VD_SP_01 | verify the user can open shop page | 1.open viswanthi.com site 2.click on shop | https://viswanthi.com/ | should open shop page | shop page is opening. | pass
VD_SP_02 | verify the user can view the filters option | 1.open viswanthi.com site 2.click on shop 3.click on filters | https://viswanthi.com/ | filter window should open. | filter window opens | pass
VD_SP_03 | verify by clicking on a colour to see whether the filter option works | 1.open viswanthi.com site 2.click on shop 3.click on filters 4.click on a colour | https://viswanthi.com/ | filtered results based on the colour should be displayed | results are shown | pass
VD_SP_04 | verify the user can select more than one colour for filtering | 1.open viswanthi.com site 2.click on shop 3.click on filters 4.click on 2 or more colours | https://viswanthi.com/ | user should be able to choose more than one color | able to choose more than ine color | pass
VD_SP_05 | verify the results shown after filtering is right | 1.open viswanthi.com site 2.click on shop 3.click on filters and apply filters | https://viswanthi.com/ | it should show the right results | results shown are right | pass
VD_SP_06 | verify the user is able to see results when clicked on orange /pink/yellow colour | 1.open viswanthi.com site 2.click on shop 3.click on filters 4.click on orange/pink color and apply filters | https://viswanthi.com/ | products should be shown | no products are showing | fail
VD_SP_07 | verify the user can deselect a color by clicking on the selected color | 1.open viswanthi.com site 2.click on shop 3.click on filters 4.click on color and click again to deselect it. | https://viswanthi.com/ | user should be able to deselect the colors | user is able to deselect the color | pass
VD_SP_08 | verify the user can clear filters | 1.open viswanthi.com site 2.click on shop 3.click on filters 4.apply some filters and then click on clear filters | https://viswanthi.com/ | it should clear all the filters | filters are cleared | pass
VD_SP_09 | check whether the user can view products in the size xxl/xxxl | 1.open viswanthi.com site 2.click on shop 3.click on filters 4. select xxl/xxxl size and apply filters | https://viswanthi.com/ | xxl/xxxl size products should be shown | products are not showing. | fail
VD_SP_10 | verify the price range slider in filter is working or not | 1.open viswanthi.com site 2.click on shop 3.click on filters 4. click on the price range slider and slide it | https://viswanthi.com/ | price range slider should work | it is working properly | pass
VD_SP_11 | verify by selecting any options in status menu from the filters | 1.open viswanthi.com site 2.click on shop 3.click on filters 4.click on any options in status. | https://viswanthi.com/ | selected options should show the results | results are not showing | fail
VD_SP_12 | verify the user can sort the products by clicking on sort by | 1.open viswanthi.com site 2.click on shop 3.click on sort by 4.click on any options | https://viswanthi.com/ | results should be shown based on sort by | results are shown | pass
VD_SP_13 | verify the user can view the product in detail when clicked on a product. | 1.open viswanthi.com site 2.click on shop 3.click on a product | https://viswanthi.com/ | product should be displayed in detail | products are displayed in detail | pass
VD_SP_14 | verify the user is able to select any size of a product | 1.open viswanthi.com site 2.click on shop 3.click on a product and select the size | https://viswanthi.com/ | user should be able to select any size | user is able to select any size | pass
VD_SP_15 | verify the user can select 2 sizes. | 1.open viswanthi.com site 2.click on shop 3.click on a product and select 2 sizes | https://viswanthi.com/ | user should not be able to select 2 sizes and | Can't select 2 sizes | pass
VD_SP_16 | verify the user can increase or decrease the no of items before adding to the cart | 1.open viswanthi.com site 2.click on shop 3.click on a product and choose the no of item. | https://viswanthi.com/ | user should be able to increase or decrease the no of items. | can increase or decrease the no of items | pass
VD_SP_17 | Verify the user can only add up to the no of available products | 1.open viswanthi.com site 2.click on shop 3.click on a product and select the no of items | https://viswanthi.com/ | user should only add upto the no of available products | user can only add upto the no of available products | pass
VD_SP_18 | verify the add to cart button is working properly | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on add to cart | https://viswanthi.com/ | add to cart should work properly | add to cart button is working properly | pass
VD_SP_19 | verify the buy now button is working properly | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on buy now | https://viswanthi.com/ | buy now button should work properly | buy now button is working properly | pass
VD_SP_20 | verify the 'ask a question' link is working | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link | https://viswanthi.com/ | ask a question window should dislay | ask a question window displays | pass
VD_SP_21 | verify the labels and fields in ask a question form are present as per the srs document. | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link | https://viswanthi.com/ | labels and fields should be present as per the srs document | labels and fields are present | pass
VD_SP_22 | verify the fields by inputing any characters | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter any inputs | https://viswanthi.com/ | user should be able to input to the fields | user is able to input into the fields | pass
VD_SP_23 | verify the name field only accepts upto a limit of characters | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link | https://viswanthi.com/ | name field should not accept more than 30 characters | name field is accepting more than 30 characters | fail
VD_SP_24 | verify the name field only accepts alphabets. | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. input any data other than alphabets in name field | https://viswanthi.com/ | name field should only accepts alphabets | name field is accepting all type of characters | fail
VD_SP_25 | verify the madatory fields are specified '*' or 'required' | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link | https://viswanthi.com/ | mandatory fields should be specified | mandatory fields are specified | pass
VD_SP_26 | verify the user is able to leave any field blank. | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5.leave the fields empty | https://viswanthi.com/ | user should not kept the fields empty | fields cannot be left empty. | pass
VD_SP_27 | verify the field accept invalid email id | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5.enter an invalid email id | https://viswanthi.com/ | email field should not accept inavlid email id | email field accepts invalid email id | fail
VD_SP_28 | verify the email field accepts without '@' | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link | https://viswanthi.com/ | email field should not accept without '@' | email field is not accepting without '@' | pass
VD_SP_29 | verify the email field with invalid email id with symbols | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter the invalid inputs | https://viswanthi.com/ | email field should not accept symbols | email field is accepting symbols other than '@' | fail
VD_SP_30 | verify the email field by entering 2 consecutive dots in th email id | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter the invalid inputs | https://viswanthi.com/ | email field should not accept more than one dot | email field is not accepting more than one dot | pass
VD_SP_31 | verify the phone number field accepts less than 10 digits | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter the phone number less than 10 digits | https://viswanthi.com/ | phone number field should not accept less than 10 digits | phone number field is accepting less than 10 digits | fail
VD_SP_32 | verify the phone number field accepts more than 10 digits | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter the phone number more than 10 digits | https://viswanthi.com/ | phone number field should not accept more than 10 digits | phone number field is accepting more than 10 digits | fail
VD_SP_33 | verify the phone number field accepts only numbers | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter some characters in phone number field | https://viswanthi.com/ | phone number field should not accept alphabets or characters | it is not accepting alphabets or characters | pass
VD_SP_34 | verify the message field by entering characters other than alphabets | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter some characters in message field | https://viswanthi.com/ | message field should not accept characters other than alphabets and numbers | it is accepting symbols | fail
VD_SP_35 | verify the send button is working | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5.click on send button. | https://viswanthi.com/ | send button should work properly | it is working properly | pass
VD_SP_36 | verify the user is able to send messages with invalid inputs | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on ask a question link 5. enter some characters in message field | https://viswanthi.com/ | message should not be send with inavlid input | message is sending with invalid inputs | fail
VD_SP_37 | verify the share icon is working or not | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on the share icon | https://viswanthi.com/ | share icon should redirect to sharing options | share icon is not working for some apps | fail
VD_SP_38 | verify the links near the share icon is working or not | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.click on the links near share icon | https://viswanthi.com/ | links should be working | links are working properly | pass
VD_SP_39 | check whether the user can add reviews without purchasing a product | 1.open viswanthi.com site 2.click on shop 3.click on a product 4.add a review | https://viswanthi.com/ | user should not be able to add review without purchasing a product | user is able to add reviews without purchasing | fail

## Registration page
VISWANTHI DESIGNS
TESTED BY:KRISHNA K.B OS:WINDOWS 11 |  |  |  | VERIFIED BY:RAKHY DATE:05/08/2024 MODULE NAME: REGISTRATION PAGE
REGISTRATION PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXCEPTED RESULT | ACTUAL RESULT | STATUS
VD_RP_01 | verify the user can view the register page while clicking on register | 1.open viswanthi designs site 2.click register on my account page | https://viswanthi.com/ | register page should be able to open | user is able to view register page | pass
VD_RP_02 | verify the user is able to input into the email field | 1.open viswanthi designs site 2.click register on my account page 3. enter into the email field | https://viswanthi.com/ | user should be able to enter inputs in email field | user is able to enter inputs in email field | pass
VD_RP_03 | check whether the user can register without entering the email id | 1.open viswanthi designs site 2.click register on my account page 3. leave the email field blank and click on setup your account | https://viswanthi.com/ | registration without email id should not be possible | registration is not possible | pass
VD_RP_04 | verify the email id field accepts an invalid email id | 1.open viswanthi designs site 2.click register on my account page 3.enter an invalid email id and click on setup your account | https://viswanthi.com/ | registration with an invalid email id should not be possible | registration is possible | fail
VD_RP_05 | check whether the user is able to register an email id without '@' symbol | 1.open viswanthi designs site 2.click register on my account page 3.enter an email id without '@' and click on setup your account | https://viswanthi.com/ | registration with an email id without '@' should not be possible | registration is not possible | pass
VD_RP_06 | verify that registration page contains a password field | 1.open viswanthi designs site 2.click register on my account page | https://viswanthi.com/ | registration page should contain password field | no password fields are present | fail
VD_RP_07 | check whether if the registration form displays the right error messages for invalid or wrong inputs. | 1.open viswanthi designs site 2.click register on my account page 3. enter invalid input in fields | https://viswanthi.com/ | error messages should be shown for invalid ior wrong inputs | error messages are shown | pass
VD_RP_08 | verify that the form prevents registration with an already registered email address. | 1.open viswanthi designs site 2.click register on my account page 3. try to register with an already registered email id | https://viswanthi.com/ | page should prevents registration with an already registered email id | user can't register with an already registered emial id | pass
VD_RP_09 | verify the privacy policy link in the register page is redirecting | 1.open viswanthi designs site 2.click register on my account page 3.click on the privacy policy link | https://viswanthi.com/ | page should redirect to privacy policy page | it is not redirecting to privacy policy | fail

## MyAccount Page
VISWANTHI DESIGNS
TESTED BY:KRISHNA K.B OS: WINDOWS 11 |  |  |  | VERIFIED BY:RAKHY DATE:05/08/2024 MODULE NAME:MY ACCOUNT PAGE
MY ACCOUNT PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXCEPTED RESULT | ACTUAL RESULT | STATUS
VD_MAP_01 | check whether user is able to view "my account" page properly | 1.open viswanthi designs site 2.click on my account after login | https://viswanthi.com/ | user should be able to view my account page | user go to the cart page | pass
VD_MAP_02 | verify the home link on my account page redirects to home page | 1.open viswanthi designs site 2.click on my account after login 3. click on the home link | https://viswanthi.com/ | it should redirect to the home page | it is redirecting to home page | pass
VD_MAP_03 | verify the logout link on my account page is working or not | 1.open viswanthi designs site 2.click on my account after login 3. click on the logout link | https://viswanthi.com/ | it should logout the user's account | logout link is working | pass
VD_MAP_04 | verify the orders link on my account page is working or not | 1.open viswanthi designs site 2.click on my account after login 3. click on the order link | https://viswanthi.com/ | it should redirects to the orders page. | orders link is working | pass
VD_MAP_05 | verify the downloads link on my account page is working or not | 1.open viswanthi designs site 2.click on my account after login 3. click on the downloads link | https://viswanthi.com/ | it should redirects to the downloads page. | downloads link is working | pass
VD_MAP_06 | verify the addresses link on my account page is working or not | 1.open viswanthi designs site 2.click on my account after login 3. click on the addresses link | https://viswanthi.com/ | it should redirects to the addresses page. | addresses link is working | pass
VD_MAP_07 | verify by clicking on 'add' in address page | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link | https://viswanthi.com/ | it should redirect to a page where we can edit or add addresses | redirecting is working | pass
VD_MAP_08 | check whether there is all the fields and labels in address adding form as per the srs document | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link | https://viswanthi.com/ | should contain all the required fields and labels | contains all the required fields and labels | pass
VD_MAP_09 | Verify that the address field is validated and that error messages are displayed when invalid information is entered. | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link | https://viswanthi.com/ | error messages should be shown when invalid information is entered | error messages are not showing | fail
VD_MAP_10 | Verify that the address form is validated and that error messages are displayed when fields are empty. | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link | https://viswanthi.com/ | error messages should be shown when fields are empty | error messages are showing | pass
VD_MAP_11 | verify the first name field accepts invalid characters such as characters and numbers | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link and enter an invalid name | https://viswanthi.com/ | error messages should be shown when the user enter an invalid name | error messages are not showing | fail
VD_MAP_12 | verify the last name field accepts invalid characters such as characters and numbers | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link and enter an invalid name | https://viswanthi.com/ | error messages should be shown when the user enter an invalid name | error messages are showing | fail
VD_MAP_13 | verify the user is able to choose the country/region | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link | https://viswanthi.com/ | user is should be able to choose country other than the default country (india) | user is not able to choose country other than the default country (india) | fail
VD_MAP_14 | verify the streetname field accepts invalid characters such as characters and numbers | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link and enter an invalid street name | https://viswanthi.com/ | error message should be shown when the user enter an invalid street name | error message should be shown when the user enter an invalid street name | fail
VD_MAP_15 | verify the apartment field accepts invalid characters such as characters and numbers | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link and enter an invalid apartment name | https://viswanthi.com/ | error message should be shown when the user enter an invalid apartment name | no error messages are shown | fail
VD_MAP_16 | verify the town/city field accepts invalid characters such as characters and numbers | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link and enter an invalid town/city name | https://viswanthi.com/ | error message should be shown when the user enter an invalid town/cityname | no error messages are shown | fail
VD_MAP_17 | verify the state field dropdown list has all the states of india | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link and open the dropdown list of states | https://viswanthi.com/ | state dropdown list should hav all the states | all the states are present in dropdown | pass
VD_MAP_18 | verify the user can add address without selecting the state | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link | https://viswanthi.com/ | error message should be shown | error message is shown | pass
VD_MAP_19 | verify the PIN field by entering alphabets and symbols | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid inputs in PIN field | https://viswanthi.com/ | error message should be shown | error message is shown | pass
VD_MAP_20 | verify the phone number field by entering less than 10 digits | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid phone number | https://viswanthi.com/ | error message should be shown | No error message shown | fail
VD_MAP_21 | verify the phone number field by entering more than 10 digits | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid phone number | https://viswanthi.com/ | error message should be shown | No error message shown | fail
VD_MAP_22 | verify the phone number field by entering alphabets or symbols | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid phone number | https://viswanthi.com/ | error message should be shown | error message is shown | pass
VD_MAP_23 | verify the email field has proper validation | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid email id | https://viswanthi.com/ | error message should be shown | error message is shown | pass
VD_MAP_24 | verify the email field accepts other symbols except '@' or '.' | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid email id with some symbols | https://viswanthi.com/ | error message should be shown | no error message is shown | fail
VD_MAP_25 | verify the save the address button works when the invalid inputs are entered | 1.open viswanthi designs site 2.click on my account after login 3. click on the address link 4.click on "add" link 5. enter invalid informations and click on the save the address button | https://viswanthi.com/ | error message should be shown | no error message is shown | fail

## BugReport
VISWANTHI DESIGNS
OS: WINDOWS 11, BROWSER: CHROME VERIFIED BY: RAKHY |  |  |  |  | DATE: 05/08/2024 TESTED BY: KRISHNA K.B
BUG REPORT
BUG ID | TEST ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS_TO_REPRODUCE | SEVIORITY | PRIORITY | SREENSHOT | STATUS
VD_BR_01 | VD_HP_02 | user should see the splash screen | while opening the site splash screen is not showing | 1.open viswanthi.com site | enhancement | P4 | n/a | new
VD_BR_02 | VD_HP_08 | should contain voice serach availability in search field | voice search is not available in search bar | 1. open the viswanthi.com site 2. click on search bar | enhancement | P3 |  | new
VD_BR_03 | VD_HP_09 | should contain image search | search bar do not contain image search | 1. open the viswanthi.com site 2. click on search bar | enhancement | P3 |  | new
VD_BR_04 | VD_HP_14 | popular search links should give results | while clicking on popular searches, no results are showing | 1. open the viswanthi.com site 2. click on search bar 3. click on any link in popular searches | major | P2 |  | new
VD_BR_05 | VD_SP_06 | products should be shown | while filtering by colours (orange/pink) no results are shown | 1. open the viswanthi.com site 2. click on shop link 3. click on filters and choose orange/pink colour in filters and apply the filter | major | P1 |  | new
VD_BR_06 | VD_SP_09 | xxl/xxxl size products should be shown | while filtering by size(xxl/xxxl),no results are shown | 1. open the viswanthi.com site 2. click on shop link 3. click on filters and choose XXL/XXXL size in filters and apply the filter | major | P2 |  | new
VD_BR_07 | VD_SP_11 | selected options should show the results | while filtering by status ( on sale/featured..),no results are shown | 1. open the viswanthi.com site 2. click on shop link 3. click on filters and choose "on sale" from status in filters and apply the filter | major | P2 |  | new
VD_BR_08 | VD_SP_23 | name field should not accept more than 30 characters | In ask a question form, name field is accepting more than 30 characters | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter a name with more than 30 characters | critical | P1 |  | new
VD_BR_09 | VD_SP_24 | name field should only accepts alphabets | In ask a question form, name field is accepting symbols and number | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter a name with symbols and numbers | critical | P1
VD_BR_10 | VD_SP_27 | email field should not accept inavlid email id | In ask a question form, email field accepts invalid email id | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter an invalid email id | critical | P1 |  | new
VD_BR_11 | VD_SP_29 | verify the email field with invalid email id with symbols | In ask a question form, email field accepts symbols other than '@' | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter an invalid email id | critical | P1 |  | new
VD_BR_12 | VD_SP_31 | phone number field should not accept less than 10 digits | phone number field is accepting less than 10 digits | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter a phone number with less than10 digits | critical | P2 |  | new
VD_BR_13 | VD_SP_32 | phone number field should not accept more than 10 digits | phone number field is accepting more than 10 digits | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter a phone number with more than 10 digits | critical | P1 |  | new
VD_BR_14 | VD_SP_34 | message field should not accept characters other than alphabets and numbers | message field is accepting symbols | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter a message with only symbols | critical | P1 |  | new
VD_BR_15 | VD_SP_36 | message should not be send with inavlid input | user is able to send message with invalid inputs | 1. open the viswanthi.com site 2. click on shop link 3. click on a product and click on the ask a question link 4. enter a message with only symbols | critical | P1 |  | new
VD_BR_16 | VD_SP_37 | share icon should redirect to sharing options | user can't click on share icon and share icon is not working for some apps | 1. open the viswanthi.com site 2. click on shop link 3. click on share icon | critical | P1 |  | new
VD_BR_17 | VD_SP_39 | user should not be able to add review without purchasing a product | user is able to add reviews without purchasing | 1. open the viswanthi.com site 2. click on shop link 3. scroll down to add reviews | critical | P1 |  | new
VD_BR_18 | VD_RP_04 | registration with an invalid email id should not be possible | registration is possible with an invalid email id | 1. open the viswanthi.com site 2. click on my account page link 3. click on register and add an invalid email | critical | P0 |  | new
VD_BR_19 | VD_RP_06 | registration page should contain password field | registration form has no password fields are present | 1. open the viswanthi.com site 2. click on my account page link 3. click on register | critical | P1 |  | new
VD_BR_20 | VD_RP_09 | clicking on privacy policy link should redirect to privacy policy page | it is not redirecting to privacy policy | 1. open the viswanthi.com site 2. click on my account page link 3. click on register 4. click on privacy policy link | major | P2 |  | new
VD_BR_21 | VD_MAP_09 | error messages should be shown when invalid information is entered | while adding invalid informations in address form ,error messages are not showing | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | critical | P0 |  | new
VD_BR_22 | VD_MAP_11 | error messages should be shown when the user enter an invalid name | while adding invalid first name in address form ,error messages are not showing | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P1 |  | new
VD_BR_23 | VD_MAP_12 | error messages should be shown when the user enter an invalid last name | while adding invalid last name in address form ,error messages are not showing | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_24 | VD_MAP_13 | user is should be able to choose country other than the default country (india) | user is not able to choose country other than the default country (india) | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_25 | VD_MAP_14 | error message should be shown when the user enter an invalid street name | error message should be shown when the user enter an invalid street name | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_26 | VD_MAP_15 | error message should be shown when the user enter an invalid apartment name | error message should be shown when the user enter an invalid apartment name | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_27 | VD_MAP_16 | error message should be shown when the user enter an invalid town/cityname | no error messages are shown when the user enter an invalid town/city name | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_28 | VD_MAP_20 | error message should be shown when the phone number field accepts less than 10 digits | no error messages are shown when the user enter less than 10 digits in phone number field | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_29 | VD_MAP_21 | error message should be shown when the phone number field accepts more than 10 digits | no error messages are shown when the user enter more than 10 digits in phone number field | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_30 | VD_MAP_24 | error message should be shown when the email field accepts other symbols except '@' or '.' | no error messages are shown when the email field accepts other symbols except '@' or '.' | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new
VD_BR_31 | VD_MAP_25 | error message should be shown when the save the address button is clicked with invalid inputs | no error messages are shown when the save the address button is clicked with invalid inputs | 1. open the viswanthi.com site 2.click on my account after login 3. click on the address link 4.click on "add" link | major | P2 |  | new

## DefectDistrubution Graph
DEFECT DISTRUBUTION GRAPH
Column1 | Column2
MODULE NAME | DEFECT DISTRUBUTION
HOME PAGE | 4
SHOP PAGE | 13
REGISTRATION PAGE | 3
MY ACCOUNT PAGE | 11

## TestReport
TEST REPORT
SL.NO | MODULE NAME | TESTCASE PASSED | TESTCASE FAILED | TOTAL TESTCASE
1 | HOME PAGE | 31 | 4 | 35
2 | SHOP PAGE | 26 | 13 | 39
3 | REGISTRATION PAGE | 6 | 3 | 9
4 | MY ACCOUNT PAGE | 14 | 11 | 25